## Slide 1: BEACON
STEERING COMMITTEE UPDATE · WEEK 1 STATUS
Supplier Integrated Management System (SIMS) Solution Assessment, Conceptual Design
Ajinomoto Philippines Corporation · Prepared by Durvah IT Consulting · 30 October 2026
Notes: Welcome and context. This is the first steering committee update, after one week of discovery (26–29 October). Logo placeholders on the top corners are for the Ajinomoto and Durvah IT Consulting logos. BEACON stands for Business Excellence through Automation, Collaboration, Optimization Network.

## Slide 2: Discovery coverage
WEEK 1 AT A GLANCE
BEACON · SteerCo Update · 30 Oct 2026
2
Session | Date | Focus
Day 1 | 26 Oct | Supplier onboarding and accreditation
Day 2 | 27 Oct | Material planning, PR–PO, ASN and goods receipt
 | 27 Oct | Invoicing, budget, DOA and supplier performance
Day 3 | 28 Oct | Supplier allocation, delivery scheduling and collaboration
 | 28 Oct | QC receiving, LIMS, rejections and return to vendor
Day 4 | 29 Oct | KPI reports and dashboards
Day 5 | 29 Oct | Current IT landscape and integration
Total |  | Scope reference: SIMS Detailed Scope (10 capability areas)
Notes: Counts come from the SIMS detailed item requirements workbook (10 sections, 87 feature lines: 53 internal, 34 supplier-facing) and the seven workshop documents. The two KPI documents are the same session and are counted once. Requirements: 24 (onboarding) + 20 (planning, PR-PO, ASN, GR) + 16 (invoicing, budget, DOA, performance) + 16 (QC and LIMS) + 18 (allocation and delivery) + 18 (KPIs) + 14 (IT integration) = 126. The Day 1 minutes record 23 onboarding requirements; the detailed note lists 24. Departments: Procurement, Supply Planning (SPLD), Finance, QA (QAD), R&D (RDD), QC (APF), IT (ITD) and the Beacon PMO; the warehouse and the LIMS project team also took part. Stakeholder count is a minimum, taken from the charter team list and workshop attendees. Technologies: SAP S/4HANA, Jedox, Infor WMS, LIMS, DataSpider, SAP Concur, Zoho Sign, Microsoft Entra ID SSO, Power BI, Azure analytics stack, HTMS portal, Citi Bank, ESS HRIS, QAD, contract repository, and Excel/email/Viber.

## Slide 3: Discovery coverage in numbers
WEEK 1 AT A GLANCE
10
Functional domains covered
87 itemised features, all discussed: 53 internal and 34 supplier-facing
4
Working sessions, 26–29 Oct
Procurement, Vendor Onboarding and risk, Material planning, invoicing, QC and LIMS, allocation, KPIs, IT etc
7
APC departments engaged
Procurement, Planning, Finance, QAD, QC, IT and R&D
20+
APC stakeholders involved
From project advisor and owner to analysts, planners and IT
5
Technologies and tools reviewed
SAP S/4HANA, Jedox, Infor WMS, LIMS, DataSpider and Concur
126
Requirements captured
Each rated Must, Should or Could for APC to confirm
50+ key challenges
7+ Templates received
BEACON · SteerCo Update · 30 Oct 2026
3
Notes: Counts come from the SIMS detailed item requirements workbook (10 sections, 87 feature lines: 53 internal, 34 supplier-facing) and the seven workshop documents. The two KPI documents are the same session and are counted once. Requirements: 24 (onboarding) + 20 (planning, PR-PO, ASN, GR) + 16 (invoicing, budget, DOA, performance) + 16 (QC and LIMS) + 18 (allocation and delivery) + 18 (KPIs) + 14 (IT integration) = 126. The Day 1 minutes record 23 onboarding requirements; the detailed note lists 24. Departments: Procurement, Supply Planning (SPLD), Finance, QA (QAD), R&D (RDD), QC (APF), IT (ITD) and the Beacon PMO; the warehouse and the LIMS project team also took part. Stakeholder count is a minimum, taken from the charter team list and workshop attendees. Technologies: SAP S/4HANA, Jedox, Infor WMS, LIMS, DataSpider, SAP Concur, Zoho Sign, Microsoft Entra ID SSO, Power BI, Azure analytics stack, HTMS portal, Citi Bank, ESS HRIS, QAD, contract repository, and Excel/email/Viber.

## Slide 4: System Process View
EXISTING SYSTEM ARCHITECTURE
BEACON · SteerCo Update · 30 Oct 2026
4
Azure
SaaS / cloud
On-premise
External
Planned
SAP Concur · invoices
SAP S/4HANA
FI and CO · finance
SD · sales
MM · purchasing, inventory
Citi Bank
payments
ESS HRIS
HR data
SLSS server
OLAP server
Azure Blob → cube
Excel pivot on PCs
sales analytics only
DataSpider middleware · Azure VM · all other SAP interfaces
HTMS portal
sales terminals
Jedox
FP&A, planning
Infor WMS
RM/PM and FG
LIMS (planned)
go-live Apr–May
no Jedox–WMS interface
Via DataSpider
Jedox (planning data), Infor WMS (real-time receipts and returns), HTMS portal.
Direct to SAP
Concur (ABAP batch, no payment status back), Citi Bank, ESS HRIS, sales analytics (CSV).
API readiness
SAP: REST and files; Jedox: API in place; WMS: expected; LIMS: unknown.
Support model
SPC IT team manages the Support and System enhancements handled by external vendors
Notes: Source: SIMS Detailed Item Requirements workbook. Each domain lists internal (APC user) features and supplier-facing (portal) features. Internal: 7+10+4+6+3+6+6+3+4+4 = 53. Supplier-facing: 5+6+2+1+2+3+5+4+4+2 = 34. Total 87 itemised features across the 10 sections of the workbook (the 8 RFP functional areas, plus Integration Capabilities and Security and Accessibility).

## Slide 5: Scope discussed: 10 domains, 87 features
PROCESS COVERAGE
53 internal and 34 supplier-facing features, each walked through with APC users
01
Supplier Qualification and Master Data
7 internal · 5 supplier
Onboarding, documents, expiry alerts, pricing
02
Procurement, Planning and Contracts
10 internal · 6 supplier
Allocation, auto-PO, delivery commitment, e-ASN
03
Supplier Performance Evaluation
4 internal · 2 supplier
Automated scorecards, reports, acknowledgment
04
Analytics and Reporting
6 internal · 1 supplier
Spend, price trends, KPI dashboards, budget
05
Communication and Collaboration
3 internal · 2 supplier
Supplier portal, secure documents, audit trail
06
Quality Management
6 internal · 3 supplier
NC database, CAR workflow, LIMS link
07
Audit and Compliance
6 internal · 5 supplier
Audit plans, checklists, findings, closure
08
Risk and Sustainability
3 internal · 4 supplier
Risk scoring, tiering, ESG, business continuity
09
Integration Capabilities
4 internal · 4 supplier
SAP S/4HANA, Jedox, Infor WMS, LIMS/QMS
10
Security and Accessibility
4 internal · 2 supplier
Role-based access, e-signature, workflows
BEACON · SteerCo Update · 30 Oct 2026
5
Notes: Source: SIMS Detailed Item Requirements workbook. Each domain lists internal (APC user) features and supplier-facing (portal) features. Internal: 7+10+4+6+3+6+6+3+4+4 = 53. Supplier-facing: 5+6+2+1+2+3+5+4+4+2 = 34. Total 87 itemised features across the 10 sections of the workbook (the 8 RFP functional areas, plus Integration Capabilities and Security and Accessibility).

## Slide 6: People, Process, Technology
WHAT WE HEARD
PEOPLE
Effort and knowledge sit with individuals
Small core user base. Processes are followed very diligently.
Multiples departments:: R&D, QA, Procurement, Finance coordination and DOA exists offline.
High reliance on manual operations and the need for automations.
PROCESS
Hand-offs happen outside the system
Stale PO data. SAP PO dates are rarely amended; real schedules live in the commitment Excel and email.
Manual chains. Onboarding, audits, NC/CAR and scorecards run on email, Excel and paper.
Returns without PO link. Returns post as stock adjustments, so debit notes are not triggered.
TECHNOLOGY
Mutiple systems running in SIlos
SAP S/4HANA is in place, but standard features go unused.
No supplier portal and central procurement analytics.
LIMS, the planning system and API readiness are still open.
Need for centralized reporting.
BEACON · SteerCo Update · 30 Oct 2026
6
Notes: People, Process and Technology are the three lenses for requirements validation now and for vendor scoring later. We suggest three additions to the scoring framework: the licence model and total cost of ownership (APC flagged hidden per-user charges on Day 1), data residency and AI control (raised in the allocation and IT sessions), and fit-to-standard versus customisation (agreed principle in the planning session). User count of about 10 is procurement (about 4), QA/QC (about 5) and one shared R&D user, still to be confirmed by APC.

## Slide 7: Existing systems are not fully utilised
GIST OF THE GAPS SO FAR
Systems are in place, but work still moves through Excel and email
SAP S/4HANA serves mainly finance postings and core features are unused
1
Manual by default. Most processes run on email and Excel.
2
Manual planning. MRP inputs, vendor allocation and PRs are prepared by hand.
3
No production orders. Consumption and finished goods are posted manually in SAP.
4
Returns to vendor. Not posted against the PO in SAP, so claims are hard to trace.
5
Delivery changes. Schedule revisions reach suppliers manually, and SAP PO dates stay unchanged.
Detail follows in the Requirement Register and Gap Analysis (4–10 Nov).
BEACON · SteerCo Update · 30 Oct 2026
7
Notes: This is a gist, not the full gap list; 78 pain points are logged across the seven sessions. Evidence: SAP is used mainly for financial postings and there is no production planning module or BOM in SAP (planning session); Jedox vendor allocation exists but is not active; MRP parameters, forecasts and the production plan are uploaded from Excel; PRs and POs, including vendor splits and prices, are keyed by hand; consumption and finished-goods receipts post with custom movement types (Z05, Z01) and no production order; returns post as stock adjustments (Z19/Z20) instead of standard return to vendor (122) against the PO; delivery revisions go to suppliers by email from the vendor commitment file and SAP PO dates are not amended.

## Slide 8: Pre-Requisite for Procurement platform
SOLUTION FOCUS
Key focus areas while designing the solution
1
Automations
2
Optimal Systems
3
Supplier Collaboration
4
Seamless Integration
5
Centralized Reporting
BEACON · SteerCo Update · 30 Oct 2026
8
Notes: This is a gist, not the full gap list; 78 pain points are logged across the seven sessions. Evidence: SAP is used mainly for financial postings and there is no production planning module or BOM in SAP (planning session); Jedox vendor allocation exists but is not active; MRP parameters, forecasts and the production plan are uploaded from Excel; PRs and POs, including vendor splits and prices, are keyed by hand; consumption and finished-goods receipts post with custom movement types (Z05, Z01) and no production order; returns post as stock adjustments (Z19/Z20) instead of standard return to vendor (122) against the PO; delivery revisions go to suppliers by email from the vendor commitment file and SAP PO dates are not amended.

## Slide 9: From discovery to conceptual design
NEXT STEPS
Phase 1 · In progress
Requirement validation
14 Oct – 10 Nov
Workshops done; supplier session 3 Nov; requirement register and gap analysis 4–10 Nov
Phase 2
Conceptual design and architecture
11 Nov – 2 Dec
Future-state architecture, conceptual design and implementation scope; presentation 2 Dec
Phase 3
Solution assessment and vendor evaluation
24 Nov – 5 Jan 2027
Platform shortlist, scripted demos and weighted scoring
Phase 4
Executive roadmap
5 – 13 Jan 2027
Implementation roadmap, budgetary estimate and risks; presentation 13 Jan
Immediate next steps, 30 Oct – 10 Nov
1
Study in detail the processes and templates shared by APC users: vendor request form, NC/CAR, audit, KPI and DOA
2
Coordinate with APC users for any clarifications to complete the Requirement Register
3
Discuss with APC Management on key decisions that might impact the Future state system landscape
BEACON · SteerCo Update · 30 Oct 2026
9
Notes: Dates follow the project charter v2.0 (16 Oct 2026). The next step is a detailed study of the process documents and templates shared by APC users, then drafting the conceptual design in collaboration with them. Phase 3 plans demos of up to five platforms (for example Ivalua, Zycus and SAP Ariba, plus others to be shortlisted with APC). The Durvah playback of our Week 1 understanding takes place on 30 Oct.

## Slide 10: THANK YOU
Notes: Dates follow the project charter v2.0 (16 Oct 2026). The next step is a detailed study of the process documents and templates shared by APC users, then drafting the conceptual design in collaboration with them. Phase 3 plans demos of up to five platforms (for example Ivalua, Zycus and SAP Ariba, plus others to be shortlisted with APC). The Durvah playback of our Week 1 understanding takes place on 30 Oct.